## ANTEDOTUM
GANTT CHART
PROGRAM: CBD: Creating Balance thru De-Stressing
COMPANY: ANTEDOTUM
| TASK NAME | START DATE | END DATE | DURATION (WORK DAYS) | TEAM MEMBER | PERCENT COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F | M | T | W | Th | F
WORK-LIFE BALANCE PLEDGE
| Write Draft of Pledge | 2021-03-22 | 2021-03-29 | 6 | Liza | 100% | bar: WEEK 1 M to WEEK 2 F
| Submit Draft to VP & CEO | 2021-03-29 | 2021-03-29 | 1 | Liza | 100%
| VP & CEO for review period | 2021-03-29 | 2021-04-02 | 5 | Hector/Karina | 100%
| VP & CEO submit edits to WM | 2021-04-02 | 2021-04-02 | 1 | Hector/Karina | 100%
| Finalize edits | 2021-04-05 | 2021-04-07 | 3 | Liza | 100% | bar: WEEK 2 M to WEEK 3 W
| Submit final copy to VP & CEO | 2021-06-21 | 2021-06-21 | 1 | Liza | 0% | bar: WEEK 2 M to WEEK 3 W
| Submit Peldge to Employees | 2021-06-23 | 2021-06-23 | 1 | Liza/Karina | 0% | bar: WEEK 3 W
| Employees Review & Sign Pledge | 2021-06-23 | 2021-06-30 | 6 | Team | 0% | bar: WEEK 3 W to WEEK 4 F
| Signed Pleadges Due to Wellness Mgr | 2021-06-30 | 2021-06-30 | 1 | Liza | 0% | bar: WEEK 4 F
NEEDS ASSESSMENT (STRESS)
| Create survery for baseline stress | 2021-06-02 | 2021-06-09 | 6 | Liza | 10%
| Submit Draft to VP & CEO | 2021-06-09 | 2021-06-09 | 1 | Liza | 0% | bar: WEEK 2 M to WEEK 3 M
| VP & CEO review period | 2021-06-09 | 2021-06-09 | 1 | Hector/Karina | 0% | bar: WEEK 2 M to WEEK 3 F
| Email Stress Suvery and Wellness Wheel to to Employees |  |  | 0 | Liza | 0%
| Employees fill out Stress Survey & Wellness Wheel |  |  | 0 | Team | 0%
| Results from SurveyMonkey reported |  |  | 0 | Liza | 0% | bar: WEEK 5 M
WEEKLEY WELLNESS TIP
| Week 1 Text | 2021-06-02 | 2021-06-02 | 1 | Liza | 100%
| Week 2 Text | 2021-06-09 | 2021-06-09 | 1 | Liza | 100%
| Week 3 Text | 2021-06-16 | 2021-06-16 | 1 | Liza | 100%
| Week 4 Text | 2021-06-23 | 2021-06-23 | 1 | Liza | 100%
| Week 5 Text | 2021-06-30 | 2021-06-30 | 1 | Liza | 0%
| Week 6 Text | 2021-07-07 | 2021-07-07 | 1 | Liza | 0%
| Week 7 Text | 2021-07-14 | 2021-07-14 | 1 | Liza | 0%
| Week 8 Text | 2021-07-21 | 2021-07-21 | 1 | Liza | 0%
| Week 9 Text | 2021-07-28 | 2021-07-28 | 1 | Liza | 0%
| Week 10 Text | 2021-08-04 | 2021-08-04 | 1 | Liza | 0%
| Week 11 Text | 2021-08-11 | 2021-08-11 | 1 | Liza | 0%
| Week 12 Text | 2021-08-18 | 2021-08-18 | 1 | Liza | 0%
WELLNESS BOX 1 |  | Feng Shui Mini-Book and Antedotum Serum & Oil Minis
| Sumbit Idea for Gift to VP & CEO | 2021-05-24 | 2021-05-24 | 1 | Liza | 100% | bar: WEEK 1 M
| VP & CEO for review period | 2021-05-24 | 2021-05-24 | 1 | Hector/Karina | 100% | bar: WEEK 1 M to WEEK 2 F
| VP & CEO approve gift | 2021-05-24 | 2021-05-24 | 1 | Hector/Karina | 100% | bar: WEEK 1 F to WEEK 2 F
| Buy Gift for 1st Zoom Session | 2021-05-24 | 2021-06-09 | 13 | Karina | 100%
| Create handwriiten notes for box | 2021-06-09 | 2021-06-14 | 4 | Liza | 100%
| Ship notes to Karina | 2021-06-14 | 2021-06-14 | 1 | Liza | 100%
| Ship Gifts for 1st Zoom Session | 2021-06-27 | 2021-06-29 | 2 | Karina | 0%
| Confirm delivery of packages | 2021-07-06 | 2021-07-06 | 1 | Liza | 0% | bar: WEEK 4 M to WEEK 4 W
ZEN ZOOM SESSION 1 |  | "Feng Shui for Home Office"
| Write draft of 1st Zen Zoom Session | 2018-04-05 | 2018-04-09 | 3 | Liza/Emilia | 50%
| Send email invite to team | 2021-06-30 | 2021-06-30 | 1 | Liza | 0%
| Conduct 1st Zoom Session | 2021-07-07 | 2021-07-07 | 1 | Liza | 0%
| Share recorded session via email | 2021-07-08 | 2021-07-08 | 1 | Liza | 0%
WELLNESS BOX 2 |  | Gua Sha Jade Stone and Lab Sample of Antedotum Relief Salve
| Sumbit Idea for Gift to VP & CEO | 2021-06-09 | 2021-06-09 | 1 | Liza | 100%
| VP & CEO for review period | 2021-06-09 | 2021-06-09 | 1 | Hector/Karina | 100%
| VP & CEO approve gift | 2021-06-09 | 2021-06-09 | 1 | Hector/Karina | 100%
| Buy Gift for 2nd Zoom Session | 2021-06-24 | 2021-07-07 | 10 | Karina | 0%
| Ship Gifts for 2nd Zoom Session | 2021-07-07 | 2021-07-07 | 1 | Karina | 0%
| Confirm delivery of packages | 2021-07-14 | 2021-07-14 | 1 | Liza | 0%
ZEN ZOOM SESSION 2 |  | "Acupressure for Relaxation"
| Write draft of 2nd Zen Zoom Session | 2021-07-07 | 2021-07-14 | 6 | Liza/Lula | 3000%
| Send email invite to team | 2021-07-14 | 2021-07-14 | 1 | Liza | 0%
| Conduct 2nd Zoom Session | 2021-07-28 | 2021-07-28 | 1 | Liza/Lula | 0%
| Share recorded session via email | 2021-07-29 | 2021-07-29 | 1 | Liza | 0%
WELLNESS BOX 3
| Submit Idea for Gift to VP & CEO | 2021-07-14 | 2021-07-14 | 1 | Liza | 0%
| VP & CEO for review period | 2021-07-14 | 2021-07-14 | 1 | Hector/Karina | 0%
| VP & CEO approve gift | 2021-07-14 | 2021-07-14 | 1 | Hector/Karina | 0%
| Buy Gift for 3rd Zoom Session | 2021-07-15 | 2021-07-19 | 3 | Karina | 0%
| Ship Gifts for 3rd Zoom Session | 2021-07-20 | 2021-07-20 | 1 | Karina | 0%
| Confirm delivery of packages | 2021-07-25 | 2021-07-25 | 0 | Liza | 0%
ZEN ZOOM SESSION 3: |  | "Boardroom Yoga" ™
| Write draft of 3rd Zen Zoom Session | 2021-07-15 | 2021-07-19 | 3 | Liza/Beth | 10%
| Send email invite to team | 2021-04-12 | 2021-04-12 | 1 | Liza | 0%
| Conduct 3rd Zoom Session | 2021-08-11 | 2021-08-11 | 1 | Liza/Beth | 0%
| Share recorded session via email | 2021-08-12 | 2021-08-12 | 1 | Liza | 0%
EVALUATION
| Data Collection | 2018-04-05 | 2018-04-09 | 3 | Liza | 10%
| Interview with Karina | 2021-04-12 | 2021-04-12 | 1 | Liza | 0%
| Share Perceived Stress Scale with Employees | 2021-06-29 | 2021-06-29 | 1 | Liza | 0%
| Share Wellness Wheel with Employees | 2021-06-29 | 2021-06-29 | 1 | Liza | 0%
Formulas:
DURATION (WORK DAYS) = NETWORKDAYS([START DATE],[END DATE])